Validation Appraisal and Verification Appraisal Guidelines for SD Accreditation Scheme

This document offers guidance for SD Auditors on how to conduct the validation and verification appraisals of the standalone micro-scale projects and activities under micro-programmes.

The Diagram 1 (located on page 7) – explains the appraisal process and the interaction between the SD Auditor, project stakeholders, Project Proponent and The Gold Standard.

SD Auditors should familiarize themselves with the following documents:

- GS Requirements

- GS Toolkit

- Annex T – Standalone Micro-Scale Scheme Rules

- Annex U – Micro-Programme Rules

- Annex W – Grievance Mechanism

- Annex H – Guidance for Do No Harm Assessment

- Annex I – Guidance on SD Indicators

- Annex AC – Indicator Questions for SD Assessment

- Annex AE – Standalone Micro-scale Scheme Flowcharts

- Annex AF – Micro-Programme Scheme Flowcharts

- Annex AQ – SD Appraisal Report – Validation Template

- Annex AR – SD Appraisal Report – Verification Template

- Annex G – Sustainable Development Checklist for Biomass, Hydro and Wind projects

- Selection of the SD Auditor

The selection of the SD Auditor will be done as described in the ‘SD Accreditation Scheme Requirements’.

- SD Validation Appraisal

The SD Auditors must follow the validation framework as detailed in The Gold Standard Rules and Procedures, paying special attention to the following items:

- Sustainable development assessment (including ‘Do No Harm’ assessment, environmental, social and economic issues, and the continuous Input & Grievance Mechanism)

- Environmental & Social Impact Assessment (ESIA)

- Stakeholder Consultation

- Stakeholder Feedback Round

- Sustainability Monitoring Plan

- SD Validation Appraisal steps

  - Desk review

Prior to the onsite visit, the SD Auditor must perform a document review in order to become familiar with the project, identifying any potential risks or aspects, relating to the Sustainable Development assessment, that will need to be checked.

The essential documents to be reviewed are, but not limited to:

- Micro-Scale PDD

- The Gold Standard LSC review and report

- Micro PoA-DD and Micro VPA-DD (only for micro-programmes)

- Design Consultation Report and Design Consultation Review (only for micro-programmes)

- Gold Standard Pre-Feasibility Assessment (if any)

- Environmental & Social Impact Assessment (ESIA)

- Any other supporting document for the SD assessment

Following the desk review SD Auditors shall prepare a ‘SD Validation Appraisal workplan’. This workplan must be submitted to the SD Management team for feedback, prior to the onsite visit. Please refer to Annex 1 for the SD Validation Appraisal workplan template.

In the case when an SD Auditor has clarifications or corrective action requests as a result of the desk review, the requests must be summarized in an annex to the workplan. The onsite visit will be used to collect necessary information. Project Proponents are not required to submit formal responses to the requests before the onsite visit; however, they must provide all the information and help to clarify these requests during the site visit.

  - Timeframe

The site visit typically takes two to three days. The preparation is crucial to obtain the optimal results and to use the time wisely. The SD Auditor must follow the SD Validation Appraisal workplan. In the case when unexpected situations are faced - e.g. relevant stakeholders identified during the site visit that were not approached during the LSC process, different methods to engage with the stakeholders, contradictions between LSC reporting and stakeholder opinion, risks/harm identified during the site visit - the SD Auditor is responsible for collecting as much information as possible to help clarify these issues. Any change observed in the project activity during the site visit shall be reported in a transparent way in the SD Validation Appraisal Report.

For a bundled approach, where a physical visit of all the project sites is unfeasible (multiple sites, site are widely dispersed e.g cookstoves or water filter projects), the site visit can be based on a sampling approach where the method is appropriately justified. Sampling methods can follow the ‘General guidelines for sampling and surveys for small-scale CDM project activities’. The sampling approach must be discussed as part of the feedback in the SD Validation workplan.

  - Site visit

The site visit will enhance the quality of the Internal Validation by facilitating a better assessment of the project impacts, enabling Auditors to directly approach the relevant stakeholders, and cross-checking the project implementation and mitigation of any anticipated risks identified with the project.

Amongst others, the SD Auditors should check the following:

- Whether all relevant stakeholders have been identified and invited to the stakeholder consultation.

- Background search about the different ethnic or minority groups living in the vicinity of the project location and consult them if appropriate.

- Ask the project participants on how they have ensured that different groups have been specifically contacted to give inputs during the stakeholder consultation meeting.

- Conduct follow-up interviews with local residents and/or NGOs to ensure that their comments from the consultation have indeed been taken into account.

- Corroborate location and implementation stage of the project activity.

- Implementation and discussion of the Continuous Input & Grievance Mechanism with the local stakeholders.

  - Reporting:

The SD Auditor must provide the SD Appraisal Report – Validation template to The Gold Standard for review within the timeframe agreed in the Service Provider agreement. The SD Appraisal template is provided in Annex 1.

The SD Validation Appraisal Report is considered complete when all clarifications and corrective requests raised by The Gold Standard have been closed satisfactorily.

The final SD Validation Appraisal Report will be made available to The Gold Standard TAC and GS NGOs Supporters at the time of the 8-week registration review as part of the registration approval process. The Appraisal report will be made publicly available following project registration.

  - Quality Control:

For details about quality control please see ‘SD Accreditation Scheme Requirements’. The Gold Standard Secretariat will review the SD Validation appraisal process and can provide feedback anytime during the process.

- SD Verification Appraisal

The SD Auditors must follow the verification framework detailed in The Gold Standard Rules and Procedures, paying special attention to the following items:

- Status of the project implementation

- Implementation of the Sustainability Monitoring Plan

- Reporting of the feedback through the Continuous Input & Grievance Mechanism and its effectiveness

- Effectiveness (or progress) of mitigation plan

- Ensure that implementation and operation of the project have not resulted in any new negative impacts or risk.

- SD Verification Appraisal steps

  - Desk review

Prior to the onsite visit, the SD Auditor must perform a desk review in order to become familiar with the activity, identifying any potential risks and the aspects, relating to the Sustainable Development assessment, that will need to be checked.

The essential documents to be reviewed are, but not limited to:

- Micro-Scale PDD

- Gold Standard LSC Review

- Micro PoA-DD and Micro VPA-DD (only for micro-programmes)

- Gold Standard Pre-Feasibility Assessment (if any)

- PoA Design Consultation Report and Design Consultation Review (only for micro PoAs)

- Final SD Validation Appraisal Report (special attention to FARs, if any)

- Monitoring report

- Data entry sheets of SD parameters (if any)

Following the desk review, the SD Auditor shall prepare a ‘SD verification workplan’. The SD Verification Appraisal workplan must be submitted to the SD Management team for feedback prior to the onsite visit. Please refer to Annex 2 for SD Verification Appraisal workplan template.

In the case when an SD Auditor has clarifications or corrections requests as a result of the desk review, the requests must be summarized in an annex to the verification workplan. The onsite visit will be used to collect the necessary information. Project Proponents are not required to submit formal responses to the requests before the onsite visit; however, they must provide all the information and correction responses to help clarify these requests during the site visit.

  - Timeframe

The site visit typically takes two to three days. The preparation is crucial to obtain the optimal results and to use the time wisely. SD Auditors must follow the SD Verification Appraisal workplan. In the case when unexpected situations are faced - e.g. relevant stakeholders identified during the site visit that were not approached during the LSC process, contradictions between the PDD and Monitoring Report, actual project conditions, and risks/harm indentified during site visit – the SD Auditor is responsible for collecting as much information as possible to clarify these issues. Any changes in the project during the site visit shall be reported in a transparent way in the SD Verification Appraisal Report.

For a bundled approach, where a physical visit to all the project sites is not feasible (multiple sites, site are widely disperse, e.g cookstoves or water filter projects), the site visit can be based on a sampling approach, when the method is appropriately justified by statistical analysis. Sampling methods can follow the ‘General guidelines for sampling and surveys for small-scale CDM project activities’. The sampling approach must be discussed as part of the feedback to the SD Verification Appraisal Workplan.

  - Site visit

The site visit will enhance the quality of the Verification by facilitating a better assessment of project impacts, enabling Auditors to directly approach the relevant stakeholders and crosschecking project implementation and identification of any potential risks due to the project activity.

Amongst others, the SD Auditors should check:

- Confirm the status of the project

- Consider conducting a few follow-up interviews with local residents and/or NGOs to ensure that they still have positive feedback about the project (focus on the operation of the project)

- Any changes that have occurred since the Validation and that have had an impact on the sustainable development aspects will need to be considered.

- In addition, the SD Auditor shall check whether any changes have occurred that may have an impact on The Gold Standard qualification of the project, particularly with reference to any potential changes in the key parameters that could lead to an overall negative impact on sustainable development of the project.

- Assess if the mitigation plan is being implemented and whether any negative impacts and risks are being effectively mitigated. Check that other negative impacts have not resulted due to the implementation and operation of the project.

  - Reporting:

The SD Auditor must provide the SD Verification Appraisal Report to The Gold Standard for review within the timeframe agreed in the Service Provider Agreement. The SD Verification template is provided in Annex 2.

The SD Verification Appraisal Report is considered complete when all the clarifications and corrective requests raised by The Gold Standard have been closed satisfactorily.

The final SD Verification Appraisal Report will be made available to The Gold Standard TAC and GS NGO Supporters at the time of the 3-week issuance review as part of the issuance approval process. The appraisal report will be made publicly available following the issuance.

  - Quality Control:

For details about quality control please see the ‘SD Accreditation Scheme Requirement’ document. The Gold Standard Secretariat will review the SD Verification appraisal process and can provide feedback anytime during the validation.

Annexes

Annex 1: SD Validation Appraisal workplan template

Annex 2: SD Verification Appraisal workplan template

Diagram 1 – Appraisal Process

http://cdm.unfccc.int/EB/050/eb50_repan30.pdf

http://cdm.unfccc.int/EB/050/eb50_repan30.pdf